## 工作表1
IOS Sheep | Project Task Lists | Version 0.1 | 2015-12-10 | 2015-12-10
| TASK Lists: | Who | When Finished ? | Status | Support Needed/Issues
RD/HW
1 | Reception unit Wifi Antenna Specification | Eric(RD) |  | 9dbi outdoor PENSON's Antenna will get it in 12/14
2 | Reception unit Bluetooth Antenna Specification | Eric(RD) |  | ??
3 | Reception unit GPS Receiver Spec | Eric(RD)
4 | Reception unit GPS Antenna Spec | Eric(RD)
5 | ID spec and proposed sketch | Eric(RD)
6 | Recception unit Solar Panel Specification | Eric(RD)
7 | Reception unit battery Specification | Eric(RD)
8 | all ADC sensors specification (temperature, mositure, wind, etc, etc) | Eric(RD)
9 | Reception Unit System Block Diagram | Eric(RD)
10 | Power management and charging circuit design | Eric(RD) |  | As the blockdiagram file
11 | Schematic detailed Diagram | Eric(RD) |  | Only draft circuits with AR 9531 & BLE no power circuits yet
12 | Bill of material List A | Eric(RD)
13 | NRE sub-contract charge(antenna, pcb layout, etc,etc,etc) | Eric(RD)
14 | NRE sub-contract labor charge(ES, EV, DVT, PV, MP ) | Eric(RD)
Smart Tag:
RD/HW | Smart Tag Bluetooth Antenna Specification | Eric(RD) |  | ??
15 | Smart TAG ID spec and proposed sketch | Eric(RD)
16 | Smart Tag Solar Panel Specification | Eric(RD) |  | No real vender yet, but I try 淨力 solar
17 | Smart Tag battery Specification | Eric(RD) |  | Need discussion, the battery as the enclosed file.
18 | Smart Tag System Block Diagram | Eric(RD) |  | As the blockdiagram file
19 | Smart Tag Power management and charging circuit design | Eric(RD)
20 | Smart Tag Schematic | Eric(RD) |  | Draft circuits
21 | Smart Tag Bill of material List B | Eric(RD)
22 | NRE sub-contract charge(antenna, pcb layout, etc,etc,etc) | Eric(RD)
23 | NRE sub-contract labor charge(ES, EV, DVT, PV, MP ) | Eric(RD)
ME/ID/Tooling items
30
Whitepaper
40 | Org Chart Revised | patrick | done
41 | Content update will base on inputs from Eric RD team | patrick | on-going | pending Eric 's input
42 | WiSilica SDK Feature list | patrick
| Development Stage | Duration | Started Date | Completed Date
| Kick-off | 1 day
| ES Phase (Engineering Sample) | 3 months
| EV Phase (Engineering Validation phase) | 3 months
| DV Phase (Design Verification phase) | 2 months
| PV Phase (Pilot Run Verification phase) | 2 months
MP Start (Mass Production phase)